Neighbourhood Priority Statement

Project Planner

| PROJECT PHASE / TASK | Proposed start date | Actual start date | Completion date | Comments |
| --- | --- | --- | --- | --- |
| Getting started |  |  |  |  |
| Agree that your town / parish want to produce a NPS and publicise the intention to produce one. |  |  | 20 July 2026 1 August 2026 on website and Landulph newsletter | This should normally be documented in the minutes of a parish meeting. You could publicise the intention in a parish newsletter or on your website; this can also be a good opportunity to ask for volunteers. |
| Submit a request to designate the neighbourhood area for your neighbourhood priority statement |  |  | 31 July 2026 | Request sent using template from CC. Parish map sent but not required. |
| Decision from LPA on designation | 2/3 weeks after receive letter |  | 20 August 2026 | We will aim to designate within 2 weeks of a complete application for a single parish area – 20 days |
| Steering group |  |  |  |  |
| Set up a working group to manage the NPS process. | 1 August 2026 |  | Initial meeting 8 September 2026 | Normally this would be made up of parish councillors and volunteers from the community. |
| Agree terms of reference (ToR) for the group |  |  |  | This should include reporting back to the parish council, how decisions are made and any funding requirements. We have a sample NDP ToR which you could adapt |
| Initial consultation and engagement |  |  |  |  |
| Initial meeting/discussion with Cornwall Council |  |  |  | An informal opportunity to better understand the process, raise questions etc Not essential |
| Agree content of initial engagement survey and methods of engagement |  |  |  | We have an initial survey template that you can adapt for your needs. Consulting digitally will make it easier to collate feedback but there are benefits to face to face or written responses as well. Encourage people to sign up to be informed about the progress of your NPS by emailing you/collecting their email address. This is important as you will need to consult again on the NPS. |
| Distribute initial survey and allow responses |  |  |  | This is the consultation period – you should allow 6 weeks for residents to respond. Don't forget to seek the views of your business community (you may want a different survey for that). |
| Analyse feedback and collate into a report |  |  |  | To ensure that your NPS reflects the views of your community and that they will support it. This should summarise the issues and concerns you have received and demonstrate how these have been considered and addressed in your neighbourhood priority statement. |
| Evidence base |  |  |  |  |
| Agree on the evidence requirements for your NPS |  |  |  | CC can provide data on a range of issues for you; you may need to supplement this with specific evidence and enhance it with local knowledge. For example, design policies for an NDP may need to be evidenced through a character statement. |
| Assess the content of gathered evidence and implications for the future of your places |  |  |  | This could cover housing, green spaces, character, design, community facilities, transport, economy, infrastructure, and sustainability. |
| Agree a plan to gather any additional evidence |  |  |  | If you have any gaps in your evidence, speak to us – we may be able to help. |
| Writing your priorities statement |  |  |  |  |
| Agree a vision for your neighbourhood area for the medium term (we suggest 20 years) |  |  |  | The results of your initial survey will help you with drafting your vision and objectives. You may want to consult separately on the vision and objectives to ensure that your community agree with the general direction of the project. |
| Use the vision to develop a number of objectives for your places |  |  |  | The vision for the future will be fundamental to your NPS, setting out how you want your places to evolve over time and how they can address current and anticipated issues. Decide whether to use the simple NPS template or the more detailed approach set out in our placeshaping toolkit. |
| Set out the medium term infrastructure priorities for your area and how growth can help to achieve them |  |  |  | Assess critical infrastructure gaps and priorities to transform your area. Set actionable goals around these priorities and identify projects to realise these goals. |
| Locations for new development (housing in particular). The preferred scale/locations for growth and the places that are not suitable for development. Can be site specific or refer to broad areas identified on maps. |  |  |  | Tell us where you think new homes (and other development) should be built. You don’t need to identify specific sites, broad locations or settlements would be fine. You can also tell us about the places that should be protected from development. |
| Identify other priorities, for example in terms of design or placemaking |  |  |  | You may also wish to develop a Design Code and/or design policies in an NDP. Tell us what would make your public spaces better. |
| Submit a draft version of your NPS to CC |  |  |  | This does not need to be a final version, we can offer advice and guidance on the content, signpost to additional evidence etc. We will consult with internal colleagues on the content. |
| Update draft NPS |  |  |  | Revise your NPS with the comments received. |
| Formal 6-week public consultation on the draft NPS |  |  |  | Please use our full list of consultees for your consultation. You will also need to consult any neighbouring town or parish councils, significant landowners, local community organisations, chambers of commerce, civic societies and local trusts and anyone else who has previously been involved with the neighbourhood priority statement. Publish your NPS on the parish website, how consultees can comment and the expiry date. |
| Review feedback |  |  |  |  |
| Update NPS |  |  |  |  |
| Submit to CC for publication |  |  |  |  |
| Submission process |  |  |  |  |
| Publication of NPS |  |  |  | NPS will be taken into account by Cornwall Council when we produce the next Cornwall Local Plan i.e. informing the policy direction. The Cornwall Local Plan will be reviewed every 5 years. |

# Links

Neighbourhood Area Designation template

Terms of Reference for SG link

Consultation and engagement GN and template

Vision and objectives GN

# Contact

Cornwall Council Neighbourhood Planning Team 
neighbourhoodplanning@cornwall.gov.uk
0300 1234 151